BOP EQUALITY ACTION PLAN – 2017/2018

## Artistic Programme

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |

## Outreach & Development – Education

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |
| Do more work with and for older people | We’ll investigate who might be interested in our new show Blanche & Butch Blanche & Butch is about older gay men. Let's see if Luminate the arts festival for older people is interested in working with us. For our Christmas show we will create relaxed performances for older people. The play is set in a home for children whose parents can't look after them. We'll chat with the older people to see if they have memories of such places | Age | Outreach plans in place by August 2017 We'll work throughout 2017 to talk to people we think might be interested | We will make sure we talk to at least 50 older people about our work We will present at least one relaxed performance | MT | Working with Luminate and LGBT Health and Wellbeing Dementia friendly performances of TS arranged |
| Increase capacity to create work accessible to disabled children | Using TS and research with schools examine how Creative Access can be applied for a younger disabled audience | Disability | May – Dec 2017 | Successful evaluation following performances | AD – GR MT | Schools work underway – broadcast of TS and other engagement scheduled |
| Increase Birds of Paradise’s knowledge of working with people from non white communities | We know that we need more information to help us increase our work with people from non white communities. We will talk first to our Board and then to other people. | Race | June 2017 |  | AD - RSG | Initial plans to identify partner for BOP Artists residency switched to work Feb 2018 in Rwanda, which built to a visit to Scotland later in 2018 |
| Get more experience of working with people from non white communities | See if we can find any information about refugees who have a disability Work with the Scottish Refugee Council to write a short report about ways we might work with disabled refugees | Race Religion Disability | February 2018 | Concise scoping paper | AD - RSG | Scooping paper not undertaken at this time but work undertaken with partners outside UK – at the culmination of this work look at Scotland partnerships and links to East Africa / refugees |

## Marketing & Communication

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |
| Increase our knowledge of the equalities make up of our audiences | Embed new terms within venue contracts to ensure equalities data is collected and fed back to us | All | June 2017 | New terms used for winter production and all show thereafter | Marianne Maxwell to lead, alongside RSG | Met with Culture Republic and Christine Hamilton – intend to host round-table discussion |
| Increase our marketing engagement with D/deaf audiences | Produce and embed BSL welcome video in to new website | Disability | July 2017 | Presence of BSL video on website | MT | Video to be commissioned from Turtlear - published |

## Finance & Administration

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |

## Partnerships & Leadership – UK & Internationally

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |
| Deepen our engagement with artists, audiences and organisations who focus on work exploring sexual orientation | Initiate conversations with Outburst (Belfast) and Homotopia (Liverpool) around coproducting 17/18 production ‘Blanche & Butch’ | Sexual orientation | By April 2017 | Solid plans in place for 17/18 coproduction | AD - RSG | Work with LGBTI orgs in Scotland key part of B&B outreach |
| Develop ways to have an ongoing engagement with disabled BAME artists and audiences | Explore long-term partnerships with organisations such as Sense Scotland | Race Religion and Belief | February 2018 | Solid plans for working with two key partners during 2018/19 | AD - RSG | Meeting to be arranged January 2018 – paused to later in 2018 due to time preassures |

## Governance

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |
| Increase representation of D/deaf and disabled people on our board | New call-out for board members with clear desire to recruit at least two board members with disability experience – targeted through appropriate routes | Disability | By October 2017 | Presence of at least two board members with disability experience | CEO - RSG | Two disabled people currently sit on our board – further development around D/deaf members underway |
| Have a more accessible governance structure to allow input from a wider range of individuals | Prepare paper for September board meeting outlining proposed changes to governance structure | All – focused on disability | September 2017 | Implementation of recommendations | CEO - GR | Easy Read Equalities Policy document created externally was not fit for purpose after testing and now creating an accessible video in consultation with users of Project Ability Glasgow |

## Employment & HR

| What result we want to see | How we’ll achieve it - Action | Who will benefit | When we’ll do this by | How we will know that we’ve done it | Who is responsible | What progress have we made |
| --- | --- | --- | --- | --- | --- | --- |
| Look at who we employ and see if there are gaps that could be filled by people from protected groups. | Audit staff and freelancers over 17/18 and explore increase in open advertising for creative work going forward | All groups | February 2018 | Track equalities make up of staff in 17/18 and compare to previous years | RSG | New disabled assistant producer |